## VCon Gantt Chart
| PROJECT TITLE |  | START DATE
| Vcon: A Remote Video Consultation of Medical and Psychological Support for Covid-19 Patients |  | 2021-03-13 |  |  | PROJECT DURATION
| PROJECT LEADER |  |  |  |  | in days
Clarence A. Bulaclac
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | [6 empty] | Not Started
1.1 | – Project Charter | Complete | Ms. KImberly Ann Dela Cruz | 2021-03-13 | 2021-03-14 | 2 |  | In Progress
1.1.1 | –– Project Charter Revisions | On Hold | Ms. KImberly Ann Dela Cruz | 2021-03-13 | 2021-03-14 | 2 |  | Complete
1.2 | – Research | Complete | Ms. Clarence Bulaclac | 2021-03-14 | 2021-03-15 | 2 |  | On Hold
1.3 | – Projections | Complete | Ms. Rosemarie Adoptante | 2021-03-14 | 2021-03-15 | 2
1.4 | – Stakeholders | Complete | Ms. KImberly Ann Dela Cruz | 2021-03-14 | 2021-03-15 | 2
1.5 | – Guidelines | Complete | Ms. Rosemarie Adoptante | 2021-03-14 | 2021-03-15 | 2
1.6 | – Project Initiation | In Progress | Ms. Clarence Bulaclac | 2021-03-15 | 2021-03-15 | 1
2 | PROJECT DEFINITION AND PLANNING |  |  | 2021-03-14
2.1 | – Scope & Goal Setting | Complete | Ms. Rosemarie Adoptante | 2021-03-14 | 2021-03-21 | 8
2.2 | – Budget | Complete | Ms. Clarence Bulaclac | 2021-03-14 | 2021-03-15 | 2
2.3 | – Communication Plan | Complete | Ms. Kimberly Ann Dela Cruz | 2021-03-14 | 2021-03-15 | 2
2.4 | – Risk Management | Complete | Ms. Clarence Bulaclac | 2021-03-16 | 2021-03-16 | 3
3 | PROJECT LAUNCH & EXECUTION
3.1 | – Status & Tracking | In Progress | Ms. KImberly Ann Dela Cruz | 2021-03-21
3.2 | – Project development stage | In Progress | Ms. Clarence Bulaclac | 2021-06-15
3.2.1 | –– Monitoring | In Progress | Ms. Rosemarie Adoptante | 2021-03-25
3.2.2 | –– Analysis and pre testing og prototype | Complete | Ms. Rosemarie Adoptante | 2021-07-16 | 2021-07-16 | 1
3.3 | – Continuing development | In Progress | Ms. Clarence Bulaclac | 2021-06-15
3.3.1 | –– Testing Evaluation | In Progress | Ms. KImberly Ann Dela Cruz | 2021-07-17 | 2021-07-17 | 1
4 | PROJECT PERFORMANCE / MONITORING |  |  | 2021-03-13
4.1 | – Project Objectives | In Progress | Ms. Kimberly Ann Dela Cruz | 2021-03-13
4.2 | – Quality Deliverables | In Progress | Ms. Rosemarie Adoptante | 2021-03-21
4.3 | – Effort & Cost Tracking | In Progress | Ms. Clarence Bulaclac | 2021-03-21
4.4 | – Project Performance | In Progress | Ms. Clarence Bulaclac | 2021-04-05
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*